## How to Use
How to Use This Community Project Milestone Tracker
Purpose | Use this workbook to track community project milestones, delivery risk, timeline movement, budget variance, resident influence evidence and TPAS accreditation readiness.
Blue input cells | Enter or update project information, dates, budgets, status, evidence and comments on the Milestone Tracker sheet.
Formula cells | Do not overwrite formula cells. These automatically calculate budget variance, days remaining, days overdue, timeline RAG, budget RAG and overall RAG.
Status dropdown | Use Not Started, In Progress, Completed, Delayed, On Hold or Cancelled.
RAG logic | Red indicates delay, overspend or evidence risk. Amber indicates approaching deadline, incomplete evidence or caution. Green indicates broadly on track.
TPAS evidence | Use the TPAS Evidence Matrix to record resident voice, communication, accountability, inclusion, impact and learning evidence.
Dashboard | The Dashboard summarises progress, budget, RAG status, delivery activity and workstream performance.
Gantt Timeline | The timeline sheet provides a simple visual view of milestone start and target dates.
Accessibility | Record evidence that engagement was accessible, inclusive and representative, including alternative formats, translation or digital inclusion support.
Accountability | Use the You Said / We Did evidence column to record how residents were updated and what changed because of their involvement.

## Milestone Tracker
Community Project Milestone Tracker – TPAS Evidence, RAG and Delivery Dashboard
Use this sheet to track milestones, deadlines, budgets, resident influence evidence, TPAS accreditation readiness and delivery risk across community projects.
Milestone ID | Project Name / Code | Workstream | Milestone Description | TPAS Theme | Customer Influence Stage | Assigned To | Sponsor / Owner | Start Date | Target Completion Date | Actual Completion Date | Status | % Completion | Dependencies | Budget Allocation (£) | Actual Expenditure (£) | Budget Variance (£) | Budget Variance % | Days Remaining | Days Overdue | Timeline RAG | Budget RAG | Evidence RAG | Overall RAG | Resident Voice Evidence | Equality / Accessibility Evidence | You Said / We Did Evidence | Notes / Issues / Decisions
M001 | COMM-001 | Resident Voice | Initial community priority workshop | Voice and Influence | Consult | Engagement Lead | Head of Communities | 2026-06-01 | 2026-06-20 |  | In Progress | 35% | None | 2500 | 1200 | 1300 | 52% | 42 | 0 | Green | Amber | Amber | Amber | Workshop notes saved; attendance list pending | Venue accessibility checked; Easy Read required | Draft feedback loop planned | Need targeted invite to younger residents
M002 | COMM-001 | Community Investment | Agree local project outcomes with residents | Community Engagement | Collaborate | Community Investment Team | Director of Customer | 2026-06-21 | 2026-07-15 |  | Not Started | 0% | M001 | 5000 | 0 | 5000 | 100% | 67 | 0 | Green | Amber | Not Evidenced | Amber | To be collected | To be confirmed | Not yet due
M003 | COMM-001 | Place Shaping | Publish You Said / We Did update | Information and Communication | Feedback | Comms Officer | Customer Influence Manager | 2026-07-16 | 2026-07-31 |  | Not Started | 0% | M002 | 1200 | 0 | 1200 | 100% | 83 | 0 | Green | Amber | Not Evidenced | Amber | Not yet due | Plain English and accessible format required | Not yet due
M004 | COMM-001 | Governance | Report impact and learning to scrutiny / board | Scrutiny and Accountability | Review | Governance Lead | Executive Sponsor | 2026-08-01 | 2026-08-30 |  | Not Started | 0% | M003 | 1000 | 0 | 1000 | 100% | 113 | 0 | Green | Amber | Not Evidenced | Amber | Not yet due | Representation analysis required | Not yet due
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
[19 empty] | 0 | Green |  |  | Green
Formulas:
Days Remaining = IF([Target Completion Date]="","",[Target Completion Date]-TODAY())
Days Overdue = IF(OR([Status]="Completed",[Target Completion Date]=""),0,MAX(0,TODAY()-[Target Completion Date]))

## Lists (hidden)
Status | RAG | TPAS Theme | Influence Stage | Workstream
Not Started | Green | Voice and Influence | Inform | Resident Voice
In Progress | Amber | Information and Communication | Consult | Community Investment
Completed | Red | Scrutiny and Accountability | Involve | Place Shaping
Delayed | Blue | Community Engagement | Collaborate | Repairs
On Hold | Not Required | Inclusion and Diversity | Co-design | Building Safety
Cancelled | Not Evidenced | Governance and Assurance | Decision | Damp and Mould
|  | Service Improvement | Feedback | Fire Safety
|  | Value for Money | Review | Neighbourhoods
|  | Learning and Impact |  | Complaints
Digital Inclusion
Leasehold / Homeownership
Procurement
Communications
Governance

## Dashboard
Community Project Milestone Tracker Dashboard
Dashboard formulas pull directly from the Milestone Tracker sheet. Update milestones and the summary will refresh in Excel.
Total Milestones |  | Completed |  | In Progress | Delayed
4 |  | 0 |  | 1 | 0
Overall Progress |  | Total Budget |  | Total Spend | Overall Variance
8.75% |  | 9700 |  | 1200 | 8500
Status | Count |  | Overall RAG | Count
Not Started | 3 |  | Green | 96
In Progress | 1 |  | Amber | 4
Completed | 0 |  | Red | 0
Delayed | 0 |  | Blue | 0
On Hold | 0
Cancelled | 0
Workstream | Milestones | Average Progress
Resident Voice | 1 | 35%
Community Investment | 1 | 0%
Place Shaping | 1 | 0%
Repairs | 0 | 0%
Building Safety | 0 | 0%
Damp and Mould | 0 | 0%
Fire Safety | 0 | 0%
Neighbourhoods | 0 | 0%
Complaints | 0 | 0%
Digital Inclusion | 0 | 0%
Leasehold / Homeownership | 0 | 0%
Procurement | 0 | 0%
Communications | 0 | 0%
Governance | 1 | 0%

## TPAS Evidence Matrix
TPAS Accreditation Evidence and Customer Influence Matrix
Use this sheet to map project milestones to TPAS-style evidence expectations, resident influence, inclusion, accountability and impact.
TPAS Area | Evidence Required | Linked Milestone ID | Current Evidence Held | Gap / Risk | Owner | Target Date | RAG
Voice and Influence | Evidence residents shaped the project scope, priorities or decisions. | [5 empty] | Amber
Information and Communication | Clear, accessible communication before, during and after the project. | [5 empty] | Amber
Scrutiny and Accountability | Evidence of reporting, review, challenge and follow-through. | [5 empty] | Amber
Inclusion and Diversity | Evidence underrepresented voices were considered and barriers reduced. | [5 empty] | Amber
Service Improvement | Evidence the project improved services, places, relationships or outcomes. | [5 empty] | Amber
Learning and Impact | Evidence learning was captured and shared for future projects. | [5 empty] | Amber
Value for Money | Evidence resources, budget and outcomes were monitored and explained. | [5 empty] | Amber

## Gantt Timeline
Milestone Timeline View
Milestone ID | Description | Start | Target | Status | 2026-06-01 | 2026-07-01 | 2026-07-31 | 2026-08-30 | 2026-09-29 | 2026-10-29 | 2026-11-28 | 2026-12-28 | 2027-01-27 | 2027-02-26
M001 | Initial community priority workshop | 46174 | 46193 | In Progress | bar: 2026-06-01
M002 | Agree local project outcomes with residents | 46194 | 46218 | Not Started | bar: 2026-07-01
M003 | Publish You Said / We Did update | 46219 | 46234 | Not Started | bar: 2026-07-31
M004 | Report impact and learning to scrutiny / board | 46235 | 46264 | Not Started | bar: 2026-08-30
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0